# QUICKBOX INTEGRATED FINANCIAL & INVENTORY MANAGEMENT SYSTEM

## Comprehensive Technical Implementation Plan & Work Breakdown Structure (WBS)

Document Version: 2.0.0
Project Phase: Integrated Architecture & Enterprise Engineering Blueprint
Target Architecture: Single Unified Relational Database (PostgreSQL / Supabase) + Event-Driven Automated General Ledger Posting Engine + Shared Master Data (parties, cost_centers) + React 19 Frontend
Target File Location: react-dashboard/Handover_Docs/Quickbox_Implementation_Plan_WBS.md
Language Standard: 100% English Technical Specification (IFRS & US GAAP Compliant)
Date: August 2026

## 1. Executive Summary & Architectural Vision

### 1.1 System Overview

The QuickBox Integrated Financial & Inventory Management System is an enterprise-grade Enterprise Resource Planning (ERP) platform engineered to unify physical warehouse operations, supply chain logistics, and double-entry general ledger accounting within a single, unified relational database.

By dismantling legacy standalone silos, QuickBox ensures that every physical movement of goods—from dock receipt and quality acceptance to internal departmental requisitions, multi-facility transfers, scrap write-offs, and customer dispatches—synchronously triggers immutable, mathematically balanced double-entry General Ledger (GL) journal vouchers (∑Debits≡∑Credits) without requiring manual bookkeeping data entry.

+---------------------------------------------------------------------------------------------------+
|                                QUICKBOX UNIFIED ENTERPRISE TOPOLOGY                               |
+---------------------------------------------------------------------------------------------------+
|                                 [ UNIFIED REACT 19 FRONTEND ]                                     |
|           ┌───────────────────────────────┬───────────────────────────────┐                       |
|           │  Inventory & Warehouse Ops    │  Finance, GL & Treasury Ops   │                       |
|           │  (StockOps, POs, Reorder, ROP)│  (Journals, AR, AP, VAT, WPS) │                       |
|           └───────────────────────┬───────┴───────┬───────────────────────┘                       |
|                                   │ REST / WS     │ REST / WS                                     |
|                                   ▼               ▼                                               |
|           ┌───────────────────────────────────────────────────────────────┐                       |
|           │              FASTAPI / NODE.JS APPLICATION BACKEND            │                       |
|           │  ┌─────────────────────────┐     ┌─────────────────────────┐  │                       |
|           │  │ Inventory Domain Engine │     │ Financial GL Core Engine│  │                       |
|           │  │ (FIFO / MAC Valuation)  │     │ (Double-Entry Posting)  │  │                       |
|           │  └────────────┬────────────┘     └────────────▲────────────┘  │                       |
|           │               │                               │               │                       |
|           │               ▼                               │               │                       |
|           │  ┌────────────────────────────────────────────┴────────────┐  │                       |
|           │  │  Transactional Outbox & Event-Driven GL Posting Bus     │  │                       |
|           │  │  (Idempotency, 3-Way Match, Variance Settlement)        │  │                       |
|           │  └─────────────────────────────────────────────────────────┘  │                       |
|           └───────────────────────────────┬───────────────────────────────┘                       |
|                                           ▼                                                       |
|           ┌───────────────────────────────────────────────────────────────┐                       |
|           │         SINGLE UNIFIED POSTGRESQL / SUPABASE DATABASE         │                       |
|           │  ┌─────────────────────────┐     ┌─────────────────────────┐  │                       |
|           │  │ Shared Master Tables    │     │ Operational Tables      │  │                       |
|           │  │ (parties, cost_centers) │     │ (items, warehouses, POs)│  │                       |
|           │  ├─────────────────────────┤     ├─────────────────────────┤  │                       |
|           │  │ Financial Core Tables   │     │ Audit & Outbox Tables   │  │                       |
|           │  │ (accounts, journals)    │     │ (outbox_events, logs)   │  │                       |
|           │  └─────────────────────────┘     └─────────────────────────┘  │                       |
|           └───────────────────────────────────────────────────────────────┘                       |
+---------------------------------------------------------------------------------------------------+

### 1.2 Core Integration Principles

- Single Unified Relational Database: Both inventory and finance domains reside within a single PostgreSQL database instance. Foreign Key constraints enforce referential integrity across sales orders, invoices, purchase orders, bills, stock movements, and journal entries.

- Shared Master Data (Zero Duplication): Eliminates redundant customer and vendor tables. A single parties table serves as the master record for suppliers, contractors, customers, and corporate partners. A unified cost_centers hierarchy anchors departmental budgets, store locations, and journal allocations.

- Automated, Zero-Touch General Ledger Workflows: Physical warehouse operations automatically formulate, balance, and post journal vouchers in real time via an event-driven transactional outbox pipeline.

- Perpetual Inventory Valuation: Real-time asset balances are maintained using deterministic First-In, First-Out (FIFO) lot queue tracking or Moving Average Cost (MAC) calculations.

- Strict Double-Entry Invariant: Every financial transaction strictly enforces ∑Debits−∑Credits=0 with zero floating-point divergence using arbitrary-precision decimal representations (NUMERIC(18, 4)).

## 2. Integrated Database Schema & Master Data Architecture

### 2.1 Shared Master Data Architecture

#### 2.1.1 Unified Party Master (parties)

To eliminate data silos, commercial counterparties are consolidated into a polymorphic parties entity supporting single-role and dual-role counterparties (e.g., vendors who also purchase goods or services):

CREATE TABLE parties (
    party_id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
    party_code VARCHAR(32) NOT NULL UNIQUE,          -- e.g. PTY-VEN-001, PTY-CUST-104
    party_type VARCHAR(20) NOT NULL CHECK (party_type IN ('ORGANIZATION', 'INDIVIDUAL')),
    legal_name VARCHAR(255) NOT NULL,
    trade_name VARCHAR(255),
    tax_registration_number VARCHAR(64),             -- VAT / Tax Identification Number
    email VARCHAR(255) NOT NULL,
    phone VARCHAR(64),
    billing_address JSONB NOT NULL,                 -- { street, city, state, postal_code, country }
    shipping_address JSONB,                         -- { street, city, state, postal_code, country }
    currency_code VARCHAR(3) NOT NULL DEFAULT 'USD',
    payment_terms VARCHAR(32) NOT NULL DEFAULT 'Net30' CHECK (payment_terms IN ('DueOnReceipt', 'Net15', 'Net30', 'Net60', 'COD')),
    credit_limit NUMERIC(18, 4) NOT NULL DEFAULT 0.0000,
    is_customer BOOLEAN NOT NULL DEFAULT FALSE,      -- Flag for AR sales interactions
    is_vendor BOOLEAN NOT NULL DEFAULT FALSE,        -- Flag for AP procurement interactions
    gl_ar_account_id UUID REFERENCES accounts(account_id), -- Specific AR sub-ledger account
    gl_ap_account_id UUID REFERENCES accounts(account_id), -- Specific AP sub-ledger account
    bank_details JSONB,                             -- { bank_name, account_num, iban, swift }
    is_active BOOLEAN NOT NULL DEFAULT TRUE,
    created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(),
    updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW()
);

CREATE INDEX idx_parties_roles ON parties(is_customer, is_vendor);
CREATE INDEX idx_parties_trn ON parties(tax_registration_number);

#### 2.1.2 Unified Cost Centers & Departments (cost_centers)

A shared hierarchy utilized by warehouses, internal requisitions, purchase budgets, and financial journal lines:

CREATE TABLE cost_centers (
    cost_center_id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
    cost_center_code VARCHAR(32) NOT NULL UNIQUE,     -- e.g. CC-100 (HQ), CC-200 (Warehouse), CC-300 (Housekeeping), CC-400 (F&B)
    cost_center_name VARCHAR(255) NOT NULL,
    parent_id UUID REFERENCES cost_centers(cost_center_id),
    manager_name VARCHAR(128),
    budget_annual NUMERIC(18, 4) NOT NULL DEFAULT 0.0000,
    is_active BOOLEAN NOT NULL DEFAULT TRUE,
    created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(),
    updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW()
);

### 2.2 Explicit Relational Foreign Key Matrix

The relational schema connects the finance and inventory modules via foreign key constraints:

| # | Originating Entity & Field | Target Master / Parent Entity & Field | Constraint Type | Operational & Financial Integration Purpose |
| --- | --- | --- | --- | --- |
| 1 | invoices.sales_order_id | sales_orders.sales_order_id | FK (ON DELETE RESTRICT) | Directly links customer commercial invoices to originating warehouse sales orders. |
| 2 | invoice_lines.so_line_id | sales_order_lines.so_line_id | FK (ON DELETE RESTRICT) | Reconciles invoiced quantities against warehouse dispatched lines; prevents over-billing. |
| 3 | invoice_lines.item_id | inventory_items.item_id | FK (ON DELETE RESTRICT) | Links billing lines to SKU master, defaulting revenue accounts and tax rates. |
| 4 | bills.purchase_order_id | purchase_orders.purchase_order_id | FK (ON DELETE RESTRICT) | Connects vendor accounts payable bills to procurement purchase orders for 3-way matching. |
| 5 | bill_lines.po_line_id | purchase_order_lines.po_line_id | FK (ON DELETE RESTRICT) | Validates billed unit prices against contracted purchase order line items; calculates PPV. |
| 6 | bill_lines.item_id | inventory_items.item_id | FK (ON DELETE RESTRICT) | Ties AP bill line items to inventory items for GR/IR accrual clearance. |
| 7 | journal_entries.stock_movement_id | stock_movements.movement_id | FK (ON DELETE RESTRICT) | Explicit link tying every automated GL journal voucher header to its triggering physical stock movement. |
| 8 | journal_lines.stock_movement_line_id | stock_movement_lines.line_id | FK (ON DELETE RESTRICT) | Granular line-item audit trail from GL journal lines down to specific physical inventory batch dispatches. |
| 9 | journal_lines.item_id | inventory_items.item_id | FK (ON DELETE RESTRICT) | Tags general ledger lines with SKU dimension for perpetual sub-ledger inventory valuation. |
| 10 | journal_lines.warehouse_id | warehouses.warehouse_id | FK (ON DELETE RESTRICT) | Tags general ledger lines with warehouse dimension for multi-facility balance sheets. |
| 11 | inventory_items.asset_account_id | accounts.account_id | FK (ON DELETE RESTRICT) | Configures balance sheet Inventory Asset account (e.g. 13110 Linens, 13120 F&B) debited on receipt. |
| 12 | inventory_items.cogs_account_id | accounts.account_id | FK (ON DELETE RESTRICT) | Configures Cost of Goods Sold account (e.g. 50110 Linens COGS, 50120 F&B COGS) debited on delivery. |
| 13 | inventory_items.revenue_account_id | accounts.account_id | FK (ON DELETE RESTRICT) | Configures Operating Revenue account (e.g. 40110 Merchandise Sales) credited on customer invoice. |
| 14 | inventory_items.inventory_adj_account_id | accounts.account_id | FK (ON DELETE RESTRICT) | Configures Variance/Shrinkage account (51900 Gain, 51950 Loss) for cycle count reconciliations. |

### 2.3 Chart of Accounts (COA) 5-Tier Structure

The unified general ledger uses a 5-tier hierarchical account code structure:

Format: C-GG-AA-SS (e.g., 13110=Class 1 [Assets], Group 3 [Inventories], Control 10 [Linens Asset])

10000 ASSETS (Normal Balance: DEBIT)
├── 11000 Cash & Cash Equivalents (1010 Operating Cash, 1020 Payroll Bank)
├── 12000 Trade & Other Receivables (11100 Accounts Receivable Control)
├── 13000 Inventories & Goods In-Transit
│   ├── 13100 Inventory Asset Control
│   │   ├── 13110 Inventory - Linens & Textiles (LIN-xxx)
│   │   ├── 13120 Inventory - Food & Beverage (FNB-xxx)
│   │   ├── 13130 Inventory - Guest Amenities & Toiletries (AMN-xxx)
│   │   ├── 13140 Inventory - Cleaning & Chemicals (CLN-xxx)
│   │   ├── 13150 Inventory - Maintenance, Repairs & Operations (MNT-xxx)
│   │   └── 13160 Inventory - Operating Equipment & Tools (EQP-xxx)
│   └── 13800 Inventory In-Transit (Inter-Facility Transfers)
└── 14000 Statutory Prepayments & Tax (14100 Input VAT / Tax Recoverable)

20000 LIABILITIES (Normal Balance: CREDIT)
├── 20000 Accounts Payable & Interim Clearing
│   ├── 20100 Accounts Payable Control (Trade Creditors)
│   ├── 20200 GR/IR Interim Clearing Account (Goods Receipt / Invoice Receipt)
│   └── 20300 Accrued Landed Costs & Inbound Freight Clearing
└── 21000 Statutory Tax Liabilities (21100 Output VAT / Tax Payable)

30000 EQUITY (Normal Balance: CREDIT)
└── 30100 Contributed Capital, 30200 Retained Earnings, 30300 Current Period P&L

40000 REVENUE (Normal Balance: CREDIT)
├── 40100 Operating Sales Revenue - Merchandise & Stock Items
├── 40200 Hospitality & Accommodation Services Revenue
└── 40900 Sales Returns & Allowances (Contra-Revenue - Normal Debit)

50000 COST OF GOODS SOLD & DIRECT INVENTORY EXPENSES (Normal Balance: DEBIT)
├── 50100 Cost of Goods Sold Control (50110 Linens, 50120 F&B, 50130 Amenities)
├── 51200 Purchase Price Variance (PPV - 3-Way Match Price Differences)
├── 51800 Inventory Scrap & Spoilage Expense
├── 51900 Inventory Gain / Count Overages (Contra-Expense - Normal Credit)
└── 51950 Inventory Shrinkage & Loss / Cycle Count Shortages

60000 OPERATING & ADMINISTRATIVE EXPENSES (Normal Balance: DEBIT)
├── 61100 Internal Departmental Operating Supplies Expense
└── 61200 Housekeeping & Cleaning Consumables Expense

## 3. Event Bus, Transactional Outbox Pattern & GL Engine Architecture

### 3.1 Transactional Outbox Pattern & Reliability

To ensure consistency between physical warehouse mutations and double-entry GL journal postings, QuickBox uses the Transactional Outbox Pattern.

+─────────────────────────────────────────────────────────────────────────────────────────────+
|                              TRANSACTIONAL OUTBOX PIPELINE                                  |
+─────────────────────────────────────────────────────────────────────────────────────────────+
|  [ Warehouse Action ] -> Click "Receive PO" or "Issue Requisition"                          |
|         │                                                                                   |
|         ▼ (ACID Transaction Scope)                                                          |
|  ┌───────────────────────────────────────────────────────────────────────────────────────┐  |
|  │ 1. INSERT INTO stock_movements / stock_movement_lines                                  │  |
|  │ 2. UPDATE inventory_cost_layers (FIFO queue) OR recalculate current_cost (MAC)        │  |
|  │ 3. INSERT INTO outbox_events (event_type, payload, status='PENDING', idempotency_key) │  |
|  └───────────────────────────────────────────────────────────────────────────────────────┘  |
|         │                                                                                   |
|         ▼ (Transaction Committed)                                                           |
|  [ Outbox Processor Daemon / CDC Worker ]                                                   |
|         │                                                                                   |
|         ▼ (Reads 'PENDING' events with SELECT ... FOR UPDATE SKIP LOCKED)                   |
|  [ Automated GL Posting Engine ]                                                            |
|         │                                                                                   |
|         ├─► Lookup Item GL Mapping (asset_account_id, cogs_account_id, etc.)                |
|         ├─► Formulate Balanced Double-Entry Journal Lines (Sum(Debit) == Sum(Credit))       |
|         ├─► Validate Fiscal Period Status == 'OPEN'                                         |
|         └─► INSERT INTO journal_entries & journal_lines (Idempotency Enforced)              |
|         │                                                                                   |
|         ▼                                                                                   |
|  ┌───────────────────────────────────────────────────────────────────────────────────────┐  |
|  │ 1. UPDATE outbox_events SET status='PROCESSED', processed_at=NOW()                    │  |
|  │ 2. UPDATE stock_movements SET journal_entry_id = journal_entries.journal_id           │  |
|  │ 3. UPDATE accounts SET current_balance = current_balance +/- amount                   │  |
|  └───────────────────────────────────────────────────────────────────────────────────────┘  |
+─────────────────────────────────────────────────────────────────────────────────────────────+

### 3.2 Outbox Event Schema & Table DDL

CREATE TABLE outbox_events (
    event_id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
    event_type VARCHAR(64) NOT NULL,                 -- e.g. INVENTORY_GOODS_RECEIPT, INVENTORY_CONSUMPTION
    aggregate_type VARCHAR(32) NOT NULL,             -- 'STOCK_MOVEMENT', 'PURCHASE_ORDER', 'INVOICE'
    aggregate_id UUID NOT NULL,                      -- Primary key of originating document
    payload JSONB NOT NULL,                          -- Full snapshot required for GL computation
    idempotency_key VARCHAR(128) NOT NULL UNIQUE,    -- SHA256(event_type + aggregate_id + sequence)
    status VARCHAR(16) NOT NULL DEFAULT 'PENDING' CHECK (status IN ('PENDING', 'PROCESSING', 'PROCESSED', 'FAILED', 'DEAD_LETTER')),
    retry_count INT NOT NULL DEFAULT 0,
    max_retries INT NOT NULL DEFAULT 5,
    error_message TEXT,
    created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(),
    processed_at TIMESTAMPTZ
);

CREATE INDEX idx_outbox_pending ON outbox_events(status, created_at) WHERE status = 'PENDING';

### 3.3 Idempotency & Deduplication Engine

- Deterministic Idempotency Key Generation:

IdempotencyKey=SHA256(eventType‖documentId‖revisionNumber)

- Database Unique Constraints: The journal_entries table enforces UNIQUE(source_module, source_document_id, source_event_type) and UNIQUE(idempotency_key).

- Dead-Letter Queue (DLQ) & Exponential Backoff: If the GL posting engine encounters a transient failure (e.g., database lock contention), the worker retries using exponential backoff:

BackoffDelay(r)=min(60,2r×1.5) seconds

- If retry_count >= 5, the event status transitions to DEAD_LETTER and an alert is dispatched to the finance operations dashboard for manual review.

## 4. Automated General Ledger Posting Rules Triggered by Inventory Events

The matrix below defines the automated double-entry postings generated by each physical warehouse and commercial transaction:

+───────────────────────────────────────────────────────────────────────────────────────────────────+
|                           PHYSICAL INVENTORY TO GL POSTING ENGINE MATRIX                          |
+───────────────────────────────────────────────────────────────────────────────────────────────────+

### 4.1 Goods Receipt from Purchase Order (GRN)

- Physical Trigger: Receiving dock personnel inspect, count, and accept inbound shipment from vendor.

- Valuation Rule: Accepted Quantity × Purchase Order Unit Price.

- Accounting Postings:

  - Debit: 13100 Inventory Asset Control (or Category Asset: 13110 Linens, 13120 F&B, 13140 Cleaning) → Increases Balance Sheet Assets

  - Credit: 20200 GR/IR Interim Clearing Account → Accrues Unbilled Liability

- Journal Dimensions: stock_movement_id, item_id, warehouse_id, cost_center_id, party_id (Vendor).

### 4.2 Inbound Landed Cost Capitalization (Freight, Customs, Insurance)

- Physical Trigger: Inbound freight carrier or customs duty invoice applied to a received shipment.

- Valuation Rule: Capitalized landed cost allocated to inventory lots based on value or weight:

ΔCosti=Line Item ValueTotal Shipment Value×Total Landed Surcharge

- Accounting Postings:

  - Debit: 13100 Inventory Asset Control → Capitalizes landed cost into inventory carrying value

  - Credit: 20300 Accrued Landed Costs & Freight Clearing → Accrues payable to logistics provider

### 4.3 Vendor Bill 3-Way Matching & Purchase Price Variance (PPV)

- Accounting Trigger: Accounts Payable receives and matches Vendor Invoice against PO and GRN.

- Valuation Rule: Billed Quantity × Invoiced Unit Price + Recoverable Input VAT.

- Case A: Exact Match (No Price Variance):

  - Debit: 20200 GR/IR Interim Clearing Account (PO Price × Qty) → Clears GR/IR Accrual

  - Debit: 14100 Input VAT / Tax Recoverable (e.g. 5% or 15% VAT) → Tax Asset

  - Credit: 20100 Accounts Payable Control (Full Invoiced Total) → Establishes Legal Trade Payable

- Case B: Unfavorable Price Variance (Bill Price > PO Price, e.g. Bill $13.00 vs PO $12.50):

  - Debit: 20200 GR/IR Interim Clearing Account (12.50×Qty) → Clears original GR/IR accrual

  - Debit: 51200 Purchase Price Variance (PPV) (0.50×Qty) → Charges cost variance to P&L

  - Debit: 14100 Input VAT / Tax Recoverable (VAT on full bill amount) → Tax Asset

  - Credit: 20100 Accounts Payable Control (Full Invoiced Total) → Trade Payable

- Case C: Favorable Price Variance (Bill Price < PO Price, e.g. Bill $12.00 vs PO $12.50):

  - Debit: 20200 GR/IR Interim Clearing Account (12.50×Qty) → Clears original GR/IR accrual

  - Debit: 14100 Input VAT / Tax Recoverable (VAT on bill amount) → Tax Asset

  - Credit: 51200 Purchase Price Variance (PPV) (0.50×Qty) → Credits favorable variance to P&L

  - Credit: 20100 Accounts Payable Control (Full Invoiced Total) → Trade Payable

### 4.4 Goods Issue for Customer Sales Order Delivery

- Physical Trigger: Warehouse dispatches picked and packed items to fulfill confirmed customer Sales Order.

- Valuation Rule: Dispatched Quantity × FIFO Cost Layer unit cost (or Moving Average Unit Cost).

- Accounting Postings:

  - Debit: 50100 Cost of Goods Sold Control (or 50110 Linens COGS, 50120 F&B COGS) → Recognizes direct expense

  - Credit: 13100 Inventory Asset Control → Relieves inventory balance sheet asset

### 4.5 Customer Commercial Invoicing & Revenue Recognition

- Commercial Trigger: Commercial sales invoice posted and sent to customer.

- Valuation Rule: Billed Quantity × Contracted Selling Unit Price + Statutory Output VAT.

- Accounting Postings:

  - Debit: 11100 Accounts Receivable Control → Accrues trade customer receivable

  - Credit: 40100 Operating Sales Revenue → Recognizes earned operating income

  - Credit: 21100 Output VAT / Tax Payable → Accrues statutory tax liability to government

### 4.6 Internal Departmental Consumption Requisition

- Physical Trigger: Storekeeper issues inventory supplies to an internal department (e.g. cleaning chemicals to Housekeeping, coffee beans to Kitchen).

- Valuation Rule: Issued Quantity × Perpetual Issue Unit Cost (FIFO / Moving Average).

- Accounting Postings:

  - Debit: 61100 Internal Department Operating Supplies Expense (or 61200 Housekeeping Consumables) → Charges operating expense tagged with specific cost_center_id

  - Credit: 13100 Inventory Asset Control (or 13140 Cleaning Chemicals Asset) → Relieves inventory asset

### 4.7 Physical Inventory Cycle Count Adjustments

- Physical Trigger: Periodic physical count reveals discrepancy against perpetual system stock.

- Case A: Physical Surplus / Overage (Physical Count > System Record):

  - Debit: 13100 Inventory Asset Control (Surplus Qty × Unit Cost) → Increases balance sheet asset

  - Credit: 51900 Inventory Gain / Count Variance → Contra-expense / operational income credit

- Case B: Physical Shortage / Shrinkage (Physical Count < System Record):

  - Debit: 51950 Inventory Shrinkage & Loss Expense (Missing Qty × Unit Cost) → Charges operational loss

  - Credit: 13100 Inventory Asset Control → Decreases balance sheet asset

### 4.8 Scrap / Spoilage / Damage / Expiry Disposal

- Physical Trigger: Quality assurance or storekeeper writes off damaged, contaminated, or expired stock.

- Valuation Rule: Scrapped Quantity × Specific Lot / Perpetual Unit Cost.

- Accounting Postings:

  - Debit: 51800 Inventory Scrap & Spoilage Expense → Disposal expense charged to P&L

  - Credit: 13100 Inventory Asset Control → Relieves damaged inventory asset

### 4.9 Inter-Warehouse Transfers & In-Transit Accounting

- Physical Trigger: Stock transferred between geographically separated warehouse facilities.

- Step A: Dispatch from Origin Warehouse:

  - Debit: 13800 Inventory In-Transit → Transfers asset into custody of carrier/transit

  - Credit: 13100-01 Inventory Asset (Main Warehouse Sub-Ledger) → Relieves origin facility

- Step B: Physical Receipt at Destination Warehouse:

  - Debit: 13100-02 Inventory Asset (Satellite Facility Sub-Ledger) → Recognizes asset at destination

  - Credit: 13800 Inventory In-Transit → Clears in-transit account

### 4.10 Return to Vendor (RTV / Purchase Return)

- Case A: Pre-Bill Return (Goods rejected at dock before AP invoice generation):

  - Debit: 20200 GR/IR Interim Clearing Account → Reverses original GR/IR accrual

  - Credit: 13100 Inventory Asset Control → Relieves returned inventory asset

- Case B: Post-Bill Return (Defective goods returned after AP invoice approved; Debit Memo issued):

  - Debit: 20100 Accounts Payable Control (Vendor Sub-Ledger) → Reduces liability to vendor

  - Credit: 13100 Inventory Asset Control → Relieves returned inventory asset

  - Credit: 14100 Input VAT / Tax Recoverable → Reverses previously claimed input tax credit

### 4.11 Customer Returns (RMA / Sales Return)

- Step A: Warehouse Restocking of Resalable Merchandise:

  - Debit: 13100 Inventory Asset Control → Reinstates inventory asset on balance sheet

  - Credit: 50100 Cost of Goods Sold Control → Reverses original COGS expense

- Step B: Finance Credit Memo Issuance:

  - Debit: 40900 Sales Returns & Allowances (Contra-Revenue) → Reduces gross revenue

  - Debit: 21100 Output VAT / Tax Payable → Reverses tax liability

  - Credit: 11100 Accounts Receivable Control (Customer Sub-Ledger) → Reduces customer balance due

## 5. Perpetual Inventory Valuation Engines: Algorithms & Mathematical Proofs

QuickBox supports both First-In, First-Out (FIFO) and Moving Average Cost (MAC) perpetual valuation models compliant with IAS 2 and US GAAP.

### 5.1 First-In, First-Out (FIFO) Perpetual Lot Queue Engine

#### 5.1.1 FIFO Lot Data Model

CREATE TABLE inventory_cost_layers (
    layer_id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
    item_id UUID NOT NULL REFERENCES inventory_items(item_id) ON DELETE RESTRICT,
    warehouse_id UUID NOT NULL REFERENCES warehouses(warehouse_id) ON DELETE RESTRICT,
    receipt_date TIMESTAMPTZ NOT NULL DEFAULT NOW(),
    original_quantity NUMERIC(18, 4) NOT NULL,
    remaining_quantity NUMERIC(18, 4) NOT NULL CHECK (remaining_quantity >= 0),
    unit_cost NUMERIC(18, 4) NOT NULL,
    source_movement_id UUID REFERENCES stock_movements(movement_id),
    is_depleted BOOLEAN NOT NULL DEFAULT FALSE,
    created_at TIMESTAMPTZ NOT NULL DEFAULT NOW()
);

CREATE INDEX idx_cost_layers_fifo ON inventory_cost_layers(item_id, warehouse_id, receipt_date) 
WHERE remaining_quantity > 0;

#### 5.1.2 FIFO Depletion Algorithm

When quantity Drequired is issued from warehouse W for item I: 1. Query active layers:

L={L1,L2,…,Lk∣Li.remaining_quantity>0, ordered by Li.receipt_date ASC}

2. Initialize Drem=Drequired and TotalValuation=0.0000. 3. For each layer Li∈L: - Compute drain amount: qi=min(Drem,Li.remaining_quantity). - Calculate layer cost contribution: ΔVi=qi×Li.unit_cost. - Update accumulators: TotalValuation←TotalValuation+ΔVi and Drem←Drem−qi. - Update database layer record: Li.remaining_quantity←Li.remaining_quantity−qi. If Li.remaining_quantity=0, set Li.is_depleted=TRUE. - Terminate loop when Drem=0. If loop finishes and Drem>0, throw INSUFFICIENT_STOCK_EXCEPTION.

#### 5.1.3 Worked Numerical Example (FIFO)

Item: FNB-100 (Coffee Beans - Espresso, Kg)
- Day 1 (Inbound Receipt 1): Receive 100 kg @ $20.00 / kg. - FIFO Queue State: Layer 1 = [100 kg @ $20.00, remaining: 100 kg, value: $2,000.00]. - Automated GL Journal Voucher (JV-GRN-001): - Dr 13120 Inventory - Food & Beverage : $2,000.00 - Cr 20200 GR/IR Interim Clearing : $2,000.00 - Day 3 (Inbound Receipt 2): Receive 50 kg @ $24.00 / kg. - FIFO Queue State: Layer 1 = [100 kg @ $20.00], Layer 2 = [50 kg @ $24.00]. - Total Stock: 150 kg, Total Book Value: $3,200.00. - Automated GL Journal Voucher (JV-GRN-002): - Dr 13120 Inventory - Food & Beverage : $1,200.00 - Cr 20200 GR/IR Interim Clearing : $1,200.00 - Day 5 (Goods Issue for Banquet): Issue 120 kg to Kitchen (cost_center_id = CC-400). - Depletion Step 1: Drain Layer 1 →100 kg×$20.00=$2,000.00 (Layer 1 depleted). - Depletion Step 2: Drain Layer 2 →20 kg×$24.00=$480.00 (Layer 2 remaining: 30 kg @ $24.00 = $720.00). - Total COGS / Expense: $2,000.00+$480.00=$2,480.00. - Automated GL Journal Voucher (JV-REQ-001): - Dr 61100 Internal Dept Operating Supplies (CC-400) : $2,480.00 - Cr 13120 Inventory - Food & Beverage : $2,480.00 - Ending State: On-hand = 30 kg @ $24.00 = $720.00 balance sheet valuation.

### 5.2 Moving Average Cost (MAC) Perpetual Valuation Engine

#### 5.2.1 Moving Average Formulas

- Receipt Recalculation Formula: Every inbound receipt recalculates the weighted unit cost Cnew:

Cnew=(Qcurrent×Ccurrent)+(Qreceived×Creceived)Qcurrent+Qreceived

- Goods Issue Valuation Formula: Outbound issues deplete stock at current moving average cost without altering unit cost:

Expense / COGS=Qissued×Ccurrent

Ending Asset Value=(Qcurrent−Qissued)×Ccurrent

#### 5.2.2 Worked Numerical Example (Moving Average)

Item: LIN-001 (Bath Towel - White, Each)
- Day 1 (Inbound Receipt 1): Receive 100 units @ $10.00 / unit. - Q1=100, C1=$10.0000, Total Asset Value = $1,000.00. - Automated GL Journal Voucher (JV-GRN-101): - Dr 13110 Inventory - Linens & Textiles : $1,000.00 - Cr 20200 GR/IR Interim Clearing : $1,000.00 - Day 3 (Inbound Receipt 2): Receive 50 units @ $13.00 / unit. - Weighted Average Calculation:

Cnew=(100×10.00)+(50×13.00)100+50=1000.00+650.00150=1650.00150=$11.0000

- Automated GL Journal Voucher (JV-GRN-102): - Dr 13110 Inventory - Linens & Textiles : $650.00 - Cr 20200 GR/IR Interim Clearing : $650.00 - Total On-Hand: 150 units @ $11.0000 = $1,650.00. - Day 5 (Goods Issue to Housekeeping): Issue 120 units to Housekeeping (CC-300). - Total Issue Cost = 120×$11.0000=$1,320.00. - Automated GL Journal Voucher (JV-REQ-101): - Dr 61200 Housekeeping Consumables Expense (CC-300) : $1,320.00 - Cr 13110 Inventory - Linens & Textiles : $1,320.00 - Ending State: Remaining Stock = 30 units @ $11.0000 = $330.00 book value.

## 6. 3-Way Matching Architecture, Tolerance Windows & Variance Management

### 6.1 3-Way Matching Process Flow

[ PURCHASE ORDER (PO) ]              [ GOODS RECEIPT NOTE (GRN) ]
    Contracted: 100 units @ $10.00        Physically Received: 100 units
    Total PO Commitment: $1,000.00        Posted to GR/IR Accrual: $1,000.00
                │                                    │
                └─────────────────┬──────────────────┘
                                  │
                                  ▼
                      [ VENDOR AP BILL (INVOICE) ]
                      Billed: 100 units @ $10.40
                      Total Billed: $1,040.00 + 5% VAT ($52.00)
                                  │
                                  ▼
                    [ 3-WAY MATCHING RECONCILIATION ]
                    ┌───────────────────────────────┐
                    │ Quantity Check: 100 == 100    │ -> PASS
                    │ Price Variance: +$0.40 / unit │ -> TOTAL VARIANCE: +$40.00 (+4.0%)
                    └─────────────┬─────────────────┘
                                  │
                  ┌───────────────┴───────────────┐
                  ▼                               ▼
       Variance <= Tolerance (2%)?      Variance > Tolerance (2%)?
                  │                               │
                  ▼                               ▼
      [ AUTOMATED GL POSTING ]          [ WORKFLOW APPROVAL HOLD ]
      Dr 20200 GR/IR       $1,000.00    Bill flagged 'MATCH_HOLD'
      Dr 51200 PPV (Opex)     $40.00    Notification sent to Procurement
      Dr 14100 Input VAT      $52.00    Payment blocked until approval
      Cr 20100 AP (Vendor) $1,092.00

### 6.2 Tolerance Rules & Automated Settlement Matrix

- Quantity Tolerance: Exact matching (±0.0%). Billed quantity cannot exceed accepted GRN quantity. Any excess quantity is placed on QUANTITY_HOLD pending warehouse verification.

- Price Tolerance Window: Configurable per vendor category:

  - Tier 1 (Auto-Post): |Bill Price−PO Price|≤2.0% OR |ΔTotal|≤$25.00. The system automatically clears GR/IR, charges/credits 51200 Purchase Price Variance (PPV), and approves the bill for payment.

  - Tier 2 (Managerial Review): Variance exceeds 2.0%. The bill is placed on PRICE_HOLD. The Procurement Manager can either accept the variance (posting to PPV) or request a revised invoice / vendor credit note.

## 7. Comprehensive 8-Phase, 32-Work-Package Work Breakdown Structure (WBS)

===================================================================================================
QUICKBOX INTEGRATED ERP IMPLEMENTATION WORK BREAKDOWN STRUCTURE (WBS)
===================================================================================================
Phase 1: Database Foundation & Unified Relational Schema (WP 1.1 - 1.4)
Phase 2: Shared Master Data & Directory Services (WP 2.1 - 2.4)
Phase 3: General Ledger Core Engine & Invariant Enforcement (WP 3.1 - 3.4)
Phase 4: Automated Inventory-to-GL Event Posting Service (WP 4.1 - 4.4)
Phase 5: Accounts Receivable (AR) & Sales Order Lifecycle (WP 5.1 - 5.4)
Phase 6: Accounts Payable (AP) & Procurement 3-Way Matching (WP 6.1 - 6.4)
Phase 7: Payroll, Fixed Assets, Tax & Financial Reporting Engine (WP 7.1 - 7.4)
Phase 8: Unified Frontend UI/UX Integration & State Architecture (WP 8.1 - 8.4)
===================================================================================================

### Phase 1: Database Foundation & Unified Relational Schema

#### WP 1.1: Core Single Database Setup & Extension Bootstrapping

- Phase: Phase 1 (Database Foundation)

- Owner: Lead Database Architect / Backend Specialist

- Duration & Predecessors: 3 Days | Predecessors: None

- Objective: Provision single PostgreSQL 16 database instance, configure connection pooling, and bootstrap UUID, pgcrypto, and audit extensions.

- Scope & Technical Specifications:

  - Initialize PostgreSQL 16 on Supabase / AWS RDS with connection pooler (PgBouncer).

  - Install required extensions: CREATE EXTENSION IF NOT EXISTS "uuid-ossp";, CREATE EXTENSION IF NOT EXISTS "pgcrypto";.

  - Configure strict transaction isolation levels (READ COMMITTED default, SERIALIZABLE for period close).

- Data Models / Tables Impacted: System database catalog, extension registry.

- API Endpoints / Service Methods: GET /api/v1/health, GET /api/v1/db/status.

- Verification & Acceptance Criteria: Automated test script verifies database connectivity, UUID generation, cryptographic hashing, and transaction rollback behavior.

#### WP 1.2: General Ledger & Fiscal Calendar DDL Migration

- Phase: Phase 1 (Database Foundation)

- Owner: Database Engineer / Financial Systems Specialist

- Duration & Predecessors: 4 Days | Predecessors: WP 1.1

- Objective: Deploy core double-entry accounting tables with balance checking constraints and fiscal period controls.

- Scope & Technical Specifications:

  - Execute DDL for accounts, fiscal_years, fiscal_periods, journal_entries, journal_lines.

  - Enforce table constraint: chk_journal_balanced CHECK (total_debit = total_credit).

  - Enforce line constraint: chk_line_side CHECK ((debit_amount > 0 AND credit_amount = 0) OR (credit_amount > 0 AND debit_amount = 0)).

- Data Models / Tables Impacted: accounts, fiscal_years, fiscal_periods, journal_entries, journal_lines.

- API Endpoints / Service Methods: Migration script 001_gl_core_schema.sql.

- Verification & Acceptance Criteria: Inserting an unbalanced journal entry (debit != credit) raises PostgreSQL check constraint violation 23514.

#### WP 1.3: Unified Master Data Schema Migration (parties, cost_centers)

- Phase: Phase 1 (Database Foundation)

- Owner: Database Engineer / Backend Specialist

- Duration & Predecessors: 3 Days | Predecessors: WP 1.2

- Objective: Deploy unified master tables for counterparties and departmental cost centers, eliminating standalone duplicate tables.

- Scope & Technical Specifications:

  - Execute DDL for parties, party_contacts, party_bank_accounts, cost_centers.

  - Create performance indexes on parties(party_code), parties(tax_registration_number), cost_centers(cost_center_code).

- Data Models / Tables Impacted: parties, party_contacts, party_bank_accounts, cost_centers.

- API Endpoints / Service Methods: Migration script 002_shared_master_data.sql.

- Verification & Acceptance Criteria: Confirm unique constraint enforcement on party_code and cost_center_code; verify shared party dual-role queries (is_customer = TRUE AND is_vendor = TRUE).

#### WP 1.4: Inventory & Operational Schema DDL Migration with Explicit Foreign Keys

- Phase: Phase 1 (Database Foundation)

- Owner: Database Engineer / Inventory Specialist

- Duration & Predecessors: 4 Days | Predecessors: WP 1.3

- Objective: Deploy warehouse, SKU catalog, purchase orders, sales orders, stock movements, and FIFO layer tables with explicit foreign keys to finance tables.

- Scope & Technical Specifications:

  - Execute DDL for warehouses, inventory_items, inventory_cost_layers, purchase_orders, purchase_order_lines, sales_orders, sales_order_lines, stock_movements, stock_movement_lines, outbox_events.

  - Add explicit foreign keys: inventory_items.asset_account_id -> accounts, invoices.sales_order_id -> sales_orders, bills.purchase_order_id -> purchase_orders, journal_entries.stock_movement_id -> stock_movements.

- Data Models / Tables Impacted: warehouses, inventory_items, inventory_cost_layers, purchase_orders, sales_orders, stock_movements, outbox_events.

- API Endpoints / Service Methods: Migration script 003_inventory_operational_schema.sql.

- Verification & Acceptance Criteria: Foreign key constraint check confirms cascading restrictions (ON DELETE RESTRICT) prevent orphaned operational or accounting records.

### Phase 2: Shared Master Data & Directory Services

#### WP 2.1: Unified Party Master API & Service Layer

- Phase: Phase 2 (Master Data & Directory Services)

- Owner: Backend Engineer (Master Data)

- Duration & Predecessors: 4 Days | Predecessors: WP 1.3

- Objective: Build CRUD REST services for unified customer/vendor management with tax validation and deduplication logic.

- Scope & Technical Specifications:

  - Implement service layer handling party creation, contact management, banking details, and credit limits.

  - Implement VAT TRN validation algorithm and auto-formatting.

- Data Models / Tables Impacted: parties, party_contacts, party_bank_accounts.

- API Endpoints / Service Methods:

  - GET /api/v1/parties?role=customer|vendor&search=...

  - POST /api/v1/parties

  - GET /api/v1/parties/{id}

  - PUT /api/v1/parties/{id}

- Verification & Acceptance Criteria: Unit tests verify creating a party with dual roles (is_customer: true, is_vendor: true) returns in both vendor procurement and customer invoicing queries.

#### WP 2.2: Hierarchical Cost Center & Department API Service

- Phase: Phase 2 (Master Data & Directory Services)

- Owner: Backend Engineer (Master Data)

- Duration & Predecessors: 3 Days | Predecessors: WP 1.3

- Objective: Build hierarchical department and cost center management service with budget enforcement.

- Scope & Technical Specifications:

  - Implement tree traversal for parent-child cost centers (CC-100 → CC-110).

  - Implement annual budget tracking and real-time expense consumption checks.

- Data Models / Tables Impacted: cost_centers.

- API Endpoints / Service Methods:

  - GET /api/v1/cost-centers

  - POST /api/v1/cost-centers

  - GET /api/v1/cost-centers/{id}/budget-utilization

- Verification & Acceptance Criteria: Cost center tree endpoint returns valid nested JSON hierarchy; utilization API correctly aggregates linked journal lines.

#### WP 2.3: Inventory Item Master Catalog with GL Account Mapping Validation

- Phase: Phase 2 (Master Data & Directory Services)

- Owner: Backend Engineer / Inventory Specialist

- Duration & Predecessors: 4 Days | Predecessors: WP 1.4, WP 2.1

- Objective: Build SKU management service that enforces valid GL account mappings (asset_account_id, cogs_account_id, revenue_account_id, inventory_adj_account_id) upon item creation.

- Scope & Technical Specifications:

  - Validate that selected GL accounts exist, are active, and match correct account types (ASSET, EXPENSE, REVENUE).

  - Support category inheritance for default account assignment.

- Data Models / Tables Impacted: inventory_items, accounts.

- API Endpoints / Service Methods:

  - GET /api/v1/inventory/items

  - POST /api/v1/inventory/items

  - PUT /api/v1/inventory/items/{id}/gl-mappings

- Verification & Acceptance Criteria: Creating an item with an invalid or closed account ID returns 422 Unprocessable Entity with explicit validation error.

#### WP 2.4: Multi-Warehouse & Storage Location Hierarchy Service

- Phase: Phase 2 (Master Data & Directory Services)

- Owner: Backend Engineer (Warehouse Domain)

- Duration & Predecessors: 3 Days | Predecessors: WP 1.4, WP 2.2

- Objective: Build warehouse and storage location directory linking physical facilities to responsible cost centers.

- Scope & Technical Specifications:

  - CRUD operations for warehouses (WH-MAIN, WH-FL1, WH-KTN) and bin locations.

  - Enforce mandatory cost_center_id association.

- Data Models / Tables Impacted: warehouses, cost_centers.

- API Endpoints / Service Methods:

  - GET /api/v1/warehouses

  - POST /api/v1/warehouses

  - GET /api/v1/warehouses/{id}/stock-summary

- Verification & Acceptance Criteria: Listing warehouses returns associated cost center metadata; stock summary computes total valuation per facility.

### Phase 3: General Ledger Core Engine & Invariant Enforcement

#### WP 3.1: Double-Entry Invariant Verification & Journal Voucher Builder Service

- Phase: Phase 3 (General Ledger Core Engine)

- Owner: Senior Financial Backend Engineer

- Duration & Predecessors: 5 Days | Predecessors: WP 1.2

- Objective: Build the core double-entry transaction builder that guarantees mathematical balance and atomic voucher posting.

- Scope & Technical Specifications:

  - Implement JournalVoucherBuilder class validating ∑Debits≡∑Credits.

  - Support arbitrary line counts, multi-currency conversion, and dimension tagging (cost_center_id, item_id, warehouse_id, party_id).

- Data Models / Tables Impacted: journal_entries, journal_lines, accounts.

- API Endpoints / Service Methods:

  - POST /api/v1/finance/journals

  - GET /api/v1/finance/journals/{id}

  - POST /api/v1/finance/journals/{id}/reverse

- Verification & Acceptance Criteria: Submitting a journal entry with 0.01 divergence throws UnbalancedJournalException; posted entries atomically update accounts.current_balance.

#### WP 3.2: Multi-Currency & Dual-FX Valuation Calculation Pipeline

- Phase: Phase 3 (General Ledger Core Engine)

- Owner: Senior Financial Backend Engineer

- Duration & Predecessors: 4 Days | Predecessors: WP 3.1

- Objective: Build exchange rate management and dual-currency transaction translation engine.

- Scope & Technical Specifications:

  - Store spot rates; translate foreign currency transactions to base functional currency (USD).

  - Calculate realized and unrealized FX gain/loss on settlements.

- Data Models / Tables Impacted: journal_entries, journal_lines, currency_rates.

- API Endpoints / Service Methods:

  - GET /api/v1/finance/fx-rates

  - POST /api/v1/finance/fx-rates

- Verification & Acceptance Criteria: Posting a EUR bill at 1.08 spot converts base debit/credit to exact USD equivalent with zero rounding drift.

#### WP 3.3: Fiscal Period Locking & Automated Year-End Closing Engine

- Phase: Phase 3 (General Ledger Core Engine)

- Owner: Senior Financial Backend Engineer

- Duration & Predecessors: 4 Days | Predecessors: WP 3.1

- Objective: Build period locking controls preventing back-dated postings and automated year-end closing P&L rollups.

- Scope & Technical Specifications:

  - Enforce period status validation (OPEN, LOCKED, CLOSED). Block transactions against LOCKED or CLOSED periods.

  - Year-end closing engine: Zero out Revenue (4xxxx) and Expense (5xxxx/6xxxx) accounts into Retained Earnings (30200).

- Data Models / Tables Impacted: fiscal_years, fiscal_periods, journal_entries, accounts.

- API Endpoints / Service Methods:

  - POST /api/v1/finance/periods/{id}/lock

  - POST /api/v1/finance/years/{id}/close

- Verification & Acceptance Criteria: Attempting to post to a locked period returns 403 Forbidden: Fiscal Period Locked; year-end close produces balanced closing voucher.

#### WP 3.4: Real-Time Account Balance Aggregation & Sub-Ledger Rollup

- Phase: Phase 3 (General Ledger Core Engine)

- Owner: Backend Engineer (Data & Analytics)

- Duration & Predecessors: 4 Days | Predecessors: WP 3.1

- Objective: Implement high-performance materialized rollups and sub-ledger reconciliation views.

- Scope & Technical Specifications:

  - Create database views aggregating balance sheet and P&L account heads by period and cost center.

  - Build sub-ledger reconciliation query validating GL 13100≡∑(Cost Layers).

- Data Models / Tables Impacted: accounts, journal_lines, database materialized views.

- API Endpoints / Service Methods:

  - GET /api/v1/finance/trial-balance

  - GET /api/v1/finance/reconcile/inventory-subledger

- Verification & Acceptance Criteria: Inventory sub-ledger reconciliation returns $0.00 variance across 10,000 synthetic transactions.

### Phase 4: Automated Inventory-to-GL Event Posting Service

#### WP 4.1: Transactional Domain Event Bus & Outbox Pipeline Setup

- Phase: Phase 4 (Automated Inventory-to-GL Engine)

- Owner: Senior Backend Systems Architect

- Duration & Predecessors: 5 Days | Predecessors: WP 1.4, WP 3.1

- Objective: Build the background polling daemon / Change Data Capture (CDC) worker that processes outbox_events reliably.

- Scope & Technical Specifications:

  - Implement concurrent worker utilizing SELECT ... FOR UPDATE SKIP LOCKED on outbox_events.

  - Implement exponential backoff retry policy and dead-letter queue routing.

- Data Models / Tables Impacted: outbox_events.

- API Endpoints / Service Methods: Worker background service (OutboxProcessorDaemon).

- Verification & Acceptance Criteria: Stress test processes 1,000 outbox events concurrently with zero duplicate GL postings and zero dropped events.

#### WP 4.2: Perpetual Valuation Engine (FIFO Cost Layers & Moving Average)

- Phase: Phase 4 (Automated Inventory-to-GL Engine)

- Owner: Senior Backend Engineer (Algorithms & Inventory)

- Duration & Predecessors: 5 Days | Predecessors: WP 1.4

- Objective: Implement FIFO layer queue depletion and Moving Average recalculation engine.

- Scope & Technical Specifications:

  - FIFO module: Ingests new layers, queries active layers by receipt_date ASC, drains quantities, updates remaining_quantity.

  - MAC module: Recomputes weighted average on receipts: Cnew=Vold+VinQold+Qin.

- Data Models / Tables Impacted: inventory_cost_layers, inventory_items.

- API Endpoints / Service Methods: InventoryValuationService.evaluateIssue(itemId, warehouseId, qty).

- Verification & Acceptance Criteria: Verified against Section 5.1 and 5.2 worked examples; outputs exact mathematical values ($2,480.00 FIFO and $1,320.00 MAC).

#### WP 4.3: Warehouse Stock Movement Event Consumers

- Phase: Phase 4 (Automated Inventory-to-GL Engine)

- Owner: Senior Financial & Inventory Engineer

- Duration & Predecessors: 6 Days | Predecessors: WP 4.1, WP 4.2

- Objective: Implement GL posting rules for all 8 physical inventory transaction types (GRN, Issue, Transfer, Adjustments, Scrap, Returns).

- Scope & Technical Specifications:

  - Implement handlers for INVENTORY_GOODS_RECEIPT, INVENTORY_CONSUMPTION, INVENTORY_TRANSFER, INVENTORY_ADJUSTMENT, INVENTORY_SCRAP, INVENTORY_RETURN_VENDOR, INVENTORY_RETURN_CUSTOMER.

  - Formulate and post balanced double-entry vouchers for each event.

- Data Models / Tables Impacted: stock_movements, journal_entries, journal_lines, accounts.

- API Endpoints / Service Methods: StockMovementPostingConsumer.handle(event).

- Verification & Acceptance Criteria: Executing each of the 8 stock operations in the warehouse UI creates a linked, balanced journal_entry with correct debit/credit accounts.

#### WP 4.4: Automated Reversal, Idempotency & Fault-Tolerant Dead Letter Queue

- Phase: Phase 4 (Automated Inventory-to-GL Engine)

- Owner: Senior Backend Systems Architect

- Duration & Predecessors: 4 Days | Predecessors: WP 4.3

- Objective: Build automated reversal mechanics for cancelled stock movements and administrative DLQ reprocessing interface.

- Scope & Technical Specifications:

  - Voiding a stock movement automatically generates a balanced mirror reversal journal entry (voucher_type = 'REVERSAL').

  - Build API to inspect, edit, and re-drive failed events in outbox_events.

- Data Models / Tables Impacted: outbox_events, journal_entries.

- API Endpoints / Service Methods:

  - GET /api/v1/finance/outbox/failed

  - POST /api/v1/finance/outbox/{id}/redrive

- Verification & Acceptance Criteria: Voiding a GRN creates exact contra-reversal JV; redriving a fixed DLQ event successfully posts to GL without duplicates.

### Phase 5: Accounts Receivable (AR) & Sales Order Lifecycle

#### WP 5.1: Sales Order to Commercial Invoice Generation Pipeline

- Phase: Phase 5 (Accounts Receivable & Sales Lifecycle)

- Owner: Backend Engineer (AR & Billing)

- Duration & Predecessors: 4 Days | Predecessors: WP 1.4, WP 2.1

- Objective: Build automated invoicing pipeline that converts confirmed warehouse Sales Orders into formal AR Commercial Invoices.

- Scope & Technical Specifications:

  - Copy lines from sales_order_lines to invoice_lines with price, discounts, and VAT calculation.

  - Link invoices.sales_order_id and update SO status to Invoiced.

- Data Models / Tables Impacted: sales_orders, sales_order_lines, invoices, invoice_lines.

- API Endpoints / Service Methods:

  - POST /api/v1/finance/invoices/from-sales-order/{soId}

  - GET /api/v1/finance/invoices

- Verification & Acceptance Criteria: Generated invoice references correct sales_order_id; line items match quantities and pricing.

#### WP 5.2: Automated Sales Revenue & Output VAT GL Posting Engine

- Phase: Phase 5 (Accounts Receivable & Sales Lifecycle)

- Owner: Senior Financial Backend Engineer

- Duration & Predecessors: 4 Days | Predecessors: WP 5.1, WP 3.1

- Objective: Synchronously post double-entry revenue vouchers upon invoice approval.

- Scope & Technical Specifications:

  - Post: Dr 11100 AR Control (Total), Cr 40100 Revenue (Subtotal), Cr 21100 Output VAT (Tax).

  - Link invoices.journal_entry_id = journal_entries.journal_id.

- Data Models / Tables Impacted: invoices, journal_entries, journal_lines.

- API Endpoints / Service Methods: POST /api/v1/finance/invoices/{id}/post.

- Verification & Acceptance Criteria: Approved invoice creates balanced GL voucher with customer party dimension and tax sub-ledger entries.

#### WP 5.3: Customer Cash Receipts & Multi-Invoice Payment Allocation Service

- Phase: Phase 5 (Accounts Receivable & Sales Lifecycle)

- Owner: Backend Engineer (Treasury & AR)

- Duration & Predecessors: 4 Days | Predecessors: WP 5.2

- Objective: Build customer payment receipt processing and multi-invoice settlement allocation engine.

- Scope & Technical Specifications:

  - Record payments from customers (Cash, Cheque, Bank Wire, Credit Card).

  - Allocate payments across multiple outstanding invoices via payment_allocations.

  - Post GL voucher: Dr 10100 Operating Cash / Bank, Cr 11100 Accounts Receivable.

- Data Models / Tables Impacted: payments, payment_allocations, invoices, journal_entries.

- API Endpoints / Service Methods:

  - POST /api/v1/finance/payments/customer-receipt

  - POST /api/v1/finance/payments/{id}/allocate

- Verification & Acceptance Criteria: Fully allocated invoice transitions status to Paid with $0.00 balance due; partial payment updates balance_due.

#### WP 5.4: Real-Time AR Aging Engine & Customer Credit Exposure Monitor

- Phase: Phase 5 (Accounts Receivable & Sales Lifecycle)

- Owner: Backend Engineer (Analytics & AR)

- Duration & Predecessors: 3 Days | Predecessors: WP 5.3

- Objective: Build real-time accounts receivable aging bucket calculation and credit limit breach detection.

- Scope & Technical Specifications:

  - Compute aging buckets: Current, 1–30 Days, 31–60 Days, 61–90 Days, 90+ Days overdue.

  - Automatically evaluate total outstanding AR against parties.credit_limit during Sales Order entry.

- Data Models / Tables Impacted: invoices, parties, sales_orders.

- API Endpoints / Service Methods:

  - GET /api/v1/reports/ar-aging

  - GET /api/v1/parties/{id}/credit-status

- Verification & Acceptance Criteria: AR aging matches sum of unpaid invoices; sales order entry rejects orders exceeding customer credit limit.

### Phase 6: Accounts Payable (AP) & Procurement 3-Way Matching

#### WP 6.1: Purchase Order to Vendor Bill 3-Way Matching Verification Service

- Phase: Phase 6 (Accounts Payable & 3-Way Matching)

- Owner: Senior Financial Backend Engineer

- Duration & Predecessors: 5 Days | Predecessors: WP 1.4, WP 2.1

- Objective: Build automated 3-way matching algorithm comparing Purchase Order, Goods Receipt Note (GRN), and Vendor Bill.

- Scope & Technical Specifications:

  - Perform line-by-line quantity and unit price comparison across PO, GRN, and AP Bill.

  - Evaluate variances against configured tolerance thresholds (±2.0%).

- Data Models / Tables Impacted: purchase_orders, purchase_order_lines, stock_movements, bills, bill_lines.

- API Endpoints / Service Methods: ThreeWayMatchingService.evaluate(billId).

- Verification & Acceptance Criteria: Quantity discrepancies > 0 flag QUANTITY_HOLD; price variances within tolerance flag AUTO_APPROVED_WITH_VARIANCE.

#### WP 6.2: GR/IR Interim Clearing Reconciliation & Purchase Price Variance (PPV) Postings

- Phase: Phase 6 (Accounts Payable & 3-Way Matching)

- Owner: Senior Financial Backend Engineer

- Duration & Predecessors: 5 Days | Predecessors: WP 6.1, WP 3.1

- Objective: Formulate and post AP Bill journal entries clearing GR/IR, booking PPV variances, and recording input VAT.

- Scope & Technical Specifications:

  - Formulate journal voucher: Dr 20200 GR/IR (at PO cost), Dr/Cr 51200 PPV (Variance), Dr 14100 Input VAT, Cr 20100 AP Control.

  - Maintain GR/IR aging report tracking unbilled receipts.

- Data Models / Tables Impacted: bills, journal_entries, journal_lines, accounts.

- API Endpoints / Service Methods:

  - POST /api/v1/finance/bills/{id}/post

  - GET /api/v1/reports/gr-ir-clearing

- Verification & Acceptance Criteria: Verified against Section 4.3 rules; GR/IR balance clears to zero and PPV is correctly charged/credited to P&L.

#### WP 6.3: Vendor Disbursement & Payment Batch Processing Service

- Phase: Phase 6 (Accounts Payable & 3-Way Matching)

- Owner: Backend Engineer (Treasury & AP)

- Duration & Predecessors: 4 Days | Predecessors: WP 6.2

- Objective: Build vendor payment batch processing, wire file generation (SEPA / ISO 20022), and AP settlement allocation.

- Scope & Technical Specifications:

  - Create payment batches for approved vendor bills.

  - Post GL voucher: Dr 20100 Accounts Payable Control, Cr 10100 Operating Cash / Bank.

- Data Models / Tables Impacted: payments, payment_allocations, bills, bank_accounts.

- API Endpoints / Service Methods:

  - POST /api/v1/finance/payments/vendor-disbursement

  - POST /api/v1/finance/payments/batch

- Verification & Acceptance Criteria: Vendor disbursement settles bill balances, updates vendor sub-ledger, and generates valid payment advice.

#### WP 6.4: Real-Time AP Aging Analysis & 1099/Tax Withholding Service

- Phase: Phase 6 (Accounts Payable & 3-Way Matching)

- Owner: Backend Engineer (Analytics & AP)

- Duration & Predecessors: 3 Days | Predecessors: WP 6.3

- Objective: Build accounts payable aging breakdown and statutory tax withholding reporting.

- Scope & Technical Specifications:

  - AP aging calculation: Current, 1–30, 31–60, 61–90, 90+ Days.

  - Track vendor 1099 / W-9 status and withholding amounts.

- Data Models / Tables Impacted: bills, parties.

- API Endpoints / Service Methods:

  - GET /api/v1/reports/ap-aging

  - GET /api/v1/reports/tax-withholding

- Verification & Acceptance Criteria: AP aging accurately aggregates outstanding bill balances; tax withholding report filters eligible vendor disbursements.

### Phase 7: Payroll, Fixed Assets, Tax & Financial Reporting Engine

#### WP 7.1: Gross-to-Net Payroll Calculation & WPS SIF File Generator

- Phase: Phase 7 (Payroll, Assets, Tax & Reporting)

- Owner: Senior Financial Backend Engineer

- Duration & Predecessors: 5 Days | Predecessors: WP 3.1

- Objective: Build monthly payroll processing, statutory deductions, Wage Protection System (WPS) SIF file generator, and automated salary journal postings.

- Scope & Technical Specifications:

  - Compute gross salary, housing/transport allowances, GOSI/social security deductions, and net salary.

  - Generate compliant Wage Protection System SIF text file for bank transmission.

  - Post GL salary voucher: Dr 63100 Salaries Expense, Cr 22100 Salaries Payable, Cr 22200 Social Security Payable.

- Data Models / Tables Impacted: employees, payroll_runs, payslips, journal_entries.

- API Endpoints / Service Methods:

  - POST /api/v1/finance/payroll/process

  - GET /api/v1/finance/payroll/{id}/wps-sif

- Verification & Acceptance Criteria: WPS SIF file passes bank format validation; payroll posting produces balanced double-entry voucher.

#### WP 7.2: Fixed Asset Capitalization & Straight-Line/Declining Depreciation Engine

- Phase: Phase 7 (Payroll, Assets, Tax & Reporting)

- Owner: Backend Engineer (Assets & Depreciation)

- Duration & Predecessors: 4 Days | Predecessors: WP 3.1

- Objective: Build fixed asset registry, useful life tracking, salvage value calculation, and automated monthly depreciation posting engine.

- Scope & Technical Specifications:

  - Implement Straight-Line and Declining Balance depreciation formulas.

  - Monthly batch job generates depreciation JV: Dr 64100 Depreciation Expense, Cr 15200 Accumulated Depreciation.

- Data Models / Tables Impacted: fixed_assets, depreciation_schedules, journal_entries.

- API Endpoints / Service Methods:

  - POST /api/v1/finance/assets

  - POST /api/v1/finance/assets/depreciate-monthly

- Verification & Acceptance Criteria: Monthly asset depreciation correctly reduces asset net book value (NBV) and posts balanced expense voucher.

#### WP 7.3: VAT Return Generation & Tax Period Settlement Pipeline

- Phase: Phase 7 (Payroll, Assets, Tax & Reporting)

- Owner: Financial Systems Specialist / Tax Accountant

- Duration & Predecessors: 4 Days | Predecessors: WP 5.2, WP 6.2

- Objective: Build statutory Value Added Tax (VAT) return calculation, box-by-box breakdown, and tax settlement journal voucher generator.

- Scope & Technical Specifications:

  - Aggregate Box 1 Standard Rated Sales (Output VAT 21100) and Box 8 Standard Rated Purchases (Input VAT 14100).

  - Calculate Net VAT Payable / Refundable: Net VAT=Output VAT−Input VAT.

  - Post settlement JV: Dr 21100 Output VAT, Cr 14100 Input VAT, Cr 21200 VAT Settlement Payable.

- Data Models / Tables Impacted: tax_periods, tax_returns, journal_entries.

- API Endpoints / Service Methods:

  - GET /api/v1/finance/tax/vat-return?periodId=...

  - POST /api/v1/finance/tax/settle

- Verification & Acceptance Criteria: VAT return box totals reconcile with AR and AP tax sub-ledgers; settlement voucher clears input and output VAT balances.

#### WP 7.4: Financial Statement Generators (Balance Sheet, P&L, Cash Flow, Trial Balance)

- Phase: Phase 7 (Payroll, Assets, Tax & Reporting)

- Owner: Senior Financial Systems Architect

- Duration & Predecessors: 5 Days | Predecessors: WP 3.4

- Objective: Build high-performance financial reporting engine generating IFRS/GAAP compliant Balance Sheet, Income Statement (P&L), Statement of Cash Flows, and Trial Balance.

- Scope & Technical Specifications:

  - Balance Sheet: Assets ≡ Liabilities + Equity.

  - Income Statement: Gross Profit = Sales Revenue - COGS - PPV ± Inventory Variance; Operating Income = Gross Profit - Operating Expenses.

  - Cash Flow: Indirect method deriving Operating, Investing, and Financing cash flows.

- Data Models / Tables Impacted: accounts, journal_lines, fiscal_periods.

- API Endpoints / Service Methods:

  - GET /api/v1/reports/balance-sheet

  - GET /api/v1/reports/income-statement

  - GET /api/v1/reports/cash-flow

- Verification & Acceptance Criteria: Trial Balance debits equal credits (∑D≡∑C); Balance Sheet is perfectly balanced; P&L net income matches balance sheet current year earnings.

### Phase 8: Unified Frontend UI/UX Integration & State Architecture

#### WP 8.1: Unified React 19 Layout, Navigation Bar & Cross-Module Context Bus

- Phase: Phase 8 (Unified Frontend UI/UX)

- Owner: Lead Frontend Architect

- Duration & Predecessors: 4 Days | Predecessors: WP 2.1, WP 3.1

- Objective: Build unified enterprise application layout, navigation sidebar, role-based routing, and cross-module notification context.

- Scope & Technical Specifications:

  - Build responsive sidebar with categorized sections: Warehouse & Stock Ops, Procurement & AP, Sales & AR, General Ledger & Accounting, Treasury, Reports.

  - Integrate React 19 Contexts (AuthContext, MasterDataContext, NotificationContext).

- Data Models / Tables Impacted: Frontend navigation routes, component layout tree.

- API Endpoints / Service Methods: UI Layout & Routing components.

- Verification & Acceptance Criteria: Navigation transitions seamlessly between Inventory views (StockOpsView, PurchaseOrdersView) and Finance views (JournalEntriesView, InvoicesView, BalanceSheetView).

#### WP 8.2: Integrated Stock Operations & Live GL Voucher Preview Modal

- Phase: Phase 8 (Unified Frontend UI/UX)

- Owner: Senior Frontend Engineer

- Duration & Predecessors: 5 Days | Predecessors: WP 4.3, WP 8.1

- Objective: Enhance StockOpsView with an interactive “Simulate & Post GL” modal allowing warehouse managers/accountants to preview the double-entry voucher before transaction execution.

- Scope & Technical Specifications:

  - Add “Preview Journal Voucher” button in batch stock transaction drawer.

  - Display debit/credit breakdown, account numbers, cost center allocations, and FIFO/MAC valuation preview.

- Data Models / Tables Impacted: react-dashboard/src/pages/StockOpsView.jsx, JournalPreviewModal.jsx.

- API Endpoints / Service Methods: POST /api/v1/inventory/movements/simulate-gl.

- Verification & Acceptance Criteria: Processing a batch stock movement displays live journal voucher preview and updates both warehouse stock tables and GL reports without page refresh.

#### WP 8.3: Procurement & Vendor Bill 3-Way Matching Data Grid Interface

- Phase: Phase 8 (Unified Frontend UI/UX)

- Owner: Frontend Engineer (Finance UI)

- Duration & Predecessors: 5 Days | Predecessors: WP 6.1, WP 8.1

- Objective: Build high-density 3-way matching data grid allowing AP clerks to compare PO, GRN, and Vendor Bill side-by-side with visual variance highlighting.

- Scope & Technical Specifications:

  - Build side-by-side comparative table with color-coded difference indicators (Green = Matched, Amber = Within Tolerance PPV, Red = Discrepancy Hold).

  - Implement one-click “Approve & Post PPV Voucher” action.

- Data Models / Tables Impacted: react-dashboard/src/pages/ThreeWayMatchingView.jsx.

- API Endpoints / Service Methods: ThreeWayMatchingGrid component.

- Verification & Acceptance Criteria: Modifying invoiced unit price in data grid dynamically computes PPV and updates projected journal voucher lines in real time.

#### WP 8.4: Real-Time Financial Notification Toasts & Immutable Audit Log Explorer

- Phase: Phase 8 (Unified Frontend UI/UX)

- Owner: Frontend Engineer (UI/UX)

- Duration & Predecessors: 3 Days | Predecessors: WP 4.4, WP 8.1

- Objective: Build real-time WebSocket toast notifications for automated GL postings and searchable audit trail explorer.

- Scope & Technical Specifications:

  - WebSocket subscription triggers toast: “Automated JV-2026-00412 Posted: $1,250.00 (PO-2026-001 Received)”.

  - Build audit log explorer with filters by User, Entity, Date Range, and Action Type.

- Data Models / Tables Impacted: react-dashboard/src/pages/AuditLogView.jsx, NotificationToast.jsx.

- API Endpoints / Service Methods: GET /api/v1/audit/logs, WebSocket /ws/notifications.

- Verification & Acceptance Criteria: Receiving a purchase order in warehouse view immediately fires toast notification in finance dashboard and writes immutable audit log.

## 8. Unified RESTful API Contract & Data Exchange Interface

| Domain | HTTP Method | Endpoint URI | Request Payload / Query Params | Response Summary & Status |
| --- | --- | --- | --- | --- |
| Master Data | GET | /api/v1/parties | ?role=customer\¦vendor&search=... | List of unified commercial counterparties (200 OK) |
| Master Data | POST | /api/v1/parties | { partyCode, legalName, trn, isCustomer, isVendor, paymentTerms, ... } | Newly created party record (201 Created) |
| Master Data | GET | /api/v1/cost-centers | ?active=true | Hierarchical departmental tree with budget utilization (200 OK) |
| Inventory | GET | /api/v1/inventory/items | ?category=Linens&status=LowStock | SKU catalog with linked GL accounts and current stock (200 OK) |
| Inventory | POST | /api/v1/inventory/movements | { movementType, warehouseId, costCenterId, refDoc, lines } | Stock movement executed + triggered GL voucher ID (201 Created) |
| Inventory | POST | /api/v1/inventory/movements/simulate-gl | { movementType, warehouseId, costCenterId, lines } | Projected balanced double-entry journal preview (200 OK) |
| Procurement | POST | /api/v1/procurement/orders | { vendorId, costCenterId, orderDate, lines: [{ itemId, qty, price }] } | Created Purchase Order (201 Created) |
| Procurement | POST | /api/v1/procurement/orders/{id}/receive | { warehouseId, acceptedLines: [{ poLineId, qtyReceived }] } | Creates GRN + emits INVENTORY_GOODS_RECEIPT event (200 OK) |
| General Ledger | GET | /api/v1/finance/journals | ?periodId=...&sourceModule=INVENTORY | List of journal entries with debit/credit verification (200 OK) |
| General Ledger | POST | /api/v1/finance/journals | { voucherType, memo, lines: [{ accountId, debit, credit, ccId, itemId }] } | Manually created/adjusting journal voucher (201 Created) |
| General Ledger | POST | /api/v1/finance/journals/{id}/reverse | { reason: "Correction of Entry" } | Balanced mirror reversal journal entry (201 Created) |
| Accounts Receivable | POST | /api/v1/finance/invoices | { customerId, salesOrderId, dueDate, lines: [{ itemId, qty, price }] } | Created AR Invoice with auto-posted revenue JV (201 Created) |
| Accounts Receivable | POST | /api/v1/finance/payments/customer-receipt | { customerId, amount, bankAccountId, allocations: [{ invoiceId, amount }] } | Customer payment recorded + AR settled (201 Created) |
| Accounts Payable | POST | /api/v1/finance/bills | { vendorId, purchaseOrderId, vendorInvoiceRef, lines } | Created AP Bill with 3-way match validation and PPV JV (201 Created) |
| Accounts Payable | POST | /api/v1/finance/payments/vendor-disbursement | { vendorId, amount, bankAccountId, allocations: [{ billId, amount }] } | Vendor payment disbursed + AP settled (201 Created) |
| Financial Reports | GET | /api/v1/reports/trial-balance | ?periodId=...&costCenterId=... | Balanced Trial Balance (∑D≡∑C) (200 OK) |
| Financial Reports | GET | /api/v1/reports/balance-sheet | ?fiscalPeriodId=... | Formal Balance Sheet with Assets ≡ Liabilities + Equity (200 OK) |
| Financial Reports | GET | /api/v1/reports/income-statement | ?fromPeriod=...&toPeriod=... | Gross Margin, COGS, PPV, Opex, and Net Income P&L (200 OK) |
| Financial Reports | GET | /api/v1/reports/gr-ir-clearing | ?unbilledDaysGte=30 | Aging report of unbilled receipts / uncleared GR/IR (200 OK) |

## 9. Database Migration Strategy, Seed Data & Rollback Protocols

### 9.1 Phased Migration Sequence

- Migration Batch 01 (Core & Master Data):

  - Extensions (uuid-ossp, pgcrypto).

  - accounts, fiscal_years, fiscal_periods.

  - parties, party_contacts, party_bank_accounts, cost_centers.

- Migration Batch 02 (Operational & Inventory):

  - warehouses, inventory_items, inventory_cost_layers.

  - purchase_orders, purchase_order_lines, sales_orders, sales_order_lines.

  - stock_movements, stock_movement_lines, outbox_events.

- Migration Batch 03 (Financial Posting & Settlement):

  - journal_entries, journal_lines (with FK to stock_movements).

  - invoices, invoice_lines, bills, bill_lines.

  - bank_accounts, payments, payment_allocations.

  - employees, payroll_runs, payslips, fixed_assets, depreciation_schedules.

- Migration Batch 04 (Constraints, Triggers & Views):

  - Check constraints: chk_journal_balanced, chk_line_side.

  - Outbox notification triggers (pg_notify for real-time daemon wakeup).

  - Real-time aggregation materialized views.

### 9.2 Standard Seed Data Suite

- Standard Chart of Accounts: Pre-loaded with 5-tier COA (10100 to 64100).

- Standard Cost Centers: CC-100 HQ / Admin, CC-200 Central Warehouse, CC-300 Housekeeping & Rooms, CC-400 Food & Beverage, CC-500 Facilities & Maintenance.

- Standard Warehouses: WH-MAIN Main Warehouse, WH-FL1 Floor 1 Storage, WH-FL2 Floor 2 Storage, WH-KTN Kitchen Store, WH-MNT Maintenance Room.

- Demo Parties: Pre-loaded with verified suppliers (Global Linens Co., CleanPro Solutions, Fresh Dairy Farms) and corporate customers (Harborline Hotel, Apex Corporate Hospitality).

- Fiscal Calendar: FY2026 initialized with 12 open monthly fiscal periods (2026-01 to 2026-12).

### 9.3 Rollback & Disaster Recovery Protocol

- Every migration step is paired with an idempotent down migration script (down.sql).

- Automated point-in-time recovery (PITR) enabled with Write-Ahead Logging (WAL) archiving to encrypted S3 / Cloud Storage every 15 minutes.

- Transactional migration runner aborts and rolls back entire batch upon encountering any DDL error.

## 10. Non-Functional Requirements, Security & Audit Compliance

### 10.1 ACID Transactional Guarantees & Concurrency Control

- Pessimistic Row-Level Locking on FIFO Layers:

SELECT * FROM inventory_cost_layers WHERE item_id = $1 FOR UPDATE;

- Prevents race conditions where concurrent goods issues attempt to deplete the same cost layer simultaneously.

- Strict Monetary Invariant: All financial amounts are stored as exact NUMERIC(18, 4). Floating point REAL or FLOAT data types are strictly prohibited to prevent IEEE-754 rounding inaccuracies.

### 10.2 Role-Based Access Control (RBAC) Permissions Matrix

| System Role | Warehouse Operations | Requisition & Issue | AR Invoicing | AP 3-Way Match | GL Journal Posting | Financial Reports |
| --- | --- | --- | --- | --- | --- | --- |
| Warehouse Storekeeper | Full Control (CRUD) | Execute Issues | View Only | View GRN Only | No Access | Stock Valuation Only |
| Department Supervisor | View Only | Create Requisitions | No Access | No Access | No Access | Dept Expense Only |
| AP / AR Clerk | View Only | View Only | Full Control | Full Control | Auto-Post Only | Aging Reports Only |
| Staff Accountant | View Movements | View Issues | Full Control | Full Control | Full Control | Full Trial Balance / P&L |
| Financial Controller / CFO | Full Audit View | Full Audit View | Full Control | Full Control | Full Approval & Lock | Full Statutory Statements |

### 10.3 Immutable Audit Trail Compliance

- Once inserted, records in journal_entries and journal_lines are immutable. Updates and deletes are blocked at the database trigger layer:

- CREATE OR REPLACE FUNCTION prevent_posted_journal_mutation()
RETURNS TRIGGER AS $$
BEGIN
    IF OLD.status = 'Posted' THEN
        RAISE EXCEPTION 'Posted journal entries are immutable. Create a reversal journal entry instead.';
    END IF;
    RETURN NEW;
END;
$$ LANGUAGE plpgsql;

- Correction of any posted transaction requires posting a counterbalancing reversal entry (voucher_type = 'REVERSAL') with full audit rationale recorded in memo.

## 11. Verification, Testing & Quality Assurance Plan

### 11.1 Automated Test Suites & Invariant Verification Matrix

- Double-Entry Balance Verification Test Suite:

  - Test scenario: Post 5,000 randomized multi-line stock movements (GRN, Issue, Transfers, Cycle Counts, Scrap, RMA).

  - Assertion: SELECT COUNT(*) FROM journal_entries WHERE total_debit != total_credit returns exactly 0.

- Sub-Ledger to General Ledger Balance Verification:

  - Test scenario: Ingest 100 POs and issue 80% of stock across multiple warehouses.

  - Assertion: SELECT SUM(remaining_quantity * unit_cost) FROM inventory_cost_layers must exactly equal SELECT current_balance FROM accounts WHERE account_code = '13100'.

- FIFO Depletion Accuracy Test:

  - Test scenario: Ingest 3 lots with price steps ($10, $15, $20); issue across boundary of Lot 1 and Lot 2.

  - Assertion: Total calculated COGS exactly matches theoretical layer drain formula down to $0.0001.

- Idempotency & Replay Attack Test:

  - Test scenario: Resend the exact same outbox_event payload 10 times to the GL Posting Engine.

  - Assertion: Database executes exactly 1 journal entry insert; subsequent 9 attempts return the existing voucher without mutating balances.

- 3-Way Matching PPV Verification Test:

  - Test scenario: PO contracted at $10.00 / unit; AP Bill received at $10.50 / unit for 100 units.

  - Assertion: Journal entry records $1,000.00 to 20200 GR/IR, $50.00 to 51200 PPV, and $1,050.00 to 20100 AP Control.

## 12. Implementation Roadmap & Milestones

Timeline: 16 Weeks (4 Months)
Phase 1: DB Foundation & Unified Schema ──► [ Weeks 1 - 2 ]
Phase 2: Master Data & Directory API   ──► [ Weeks 3 - 4 ]
Phase 3: General Ledger Core Engine    ──► [ Weeks 5 - 6 ]
Phase 4: Inventory-to-GL Event Bus     ──► [ Weeks 7 - 9 ]
Phase 5: AR & Sales Order Lifecycle    ──► [ Weeks 10 - 11 ]
Phase 6: AP & 3-Way Matching           ──► [ Weeks 12 - 13 ]
Phase 7: Payroll, Tax & Reporting      ──► [ Weeks 14 - 15 ]
Phase 8: UI Integration & UAT Go-Live  ──► [ Week 16 ]

End of Technical Implementation Plan & Work Breakdown Structure (WBS).